## Sheet1
Task | Project Manager | Business Analyst | Software Developer | Data Scientists | Agricultural Experts | UI/UX Designers | QA/Tester | Field Technician | Marketing/Sales Team | Hardware Engineers
Project plan | R
Define project scope | R
Establish project timeline | R
Allocate resources | R
Monitor project progress | R
Market analysis |  | R |  | S
Feasibility study |  | R |  | S |  |  | S
Requirements gathering |  | R | S | S | S
Research IoT sensors |  |  |  |  | R |  |  |  | S
Develop ML algorithms |  |  | R | R
Design user interface | [5 empty] | R
Test and validate algorithms |  | S | R | R |  |  | R
Design IoT sensors |  |  |  |  | R |  |  |  |  | R
Develop prototypes |  |  |  |  | R |  |  |  | S
Finalize sensor design |  |  |  |  | R |  |  |  | S
Manufacture sensors |  |  |  |  | R |  |  |  | S
Develop backend infrastructure |  |  | R | R
Develop mobile application |  |  | R
Integrate sensors |  |  | R | [5 empty] | S
Conduct testing and debugging |  |  | R |  |  |  | R |  | S
Install IoT sensors | [7 empty] | R
Conduct training sessions | [7 empty] | R | S
Monitor system performance | [7 empty] | R | S
Collect feedback | [7 empty] | R | S
Develop marketing materials | [8 empty] | R | S
Acquire customers | [8 empty] | R | S
Evaluate impact |  | R | S |  |  |  |  | S
Make adjustments and improvements |  | S | R | S
Document project processes |  | R
Prepare progress reports | R | S
R= Responsible S= Support